Operations & Training Risk Management Plan
Author: Project Manager / Status: Draft	Created:Aug 18 2022 / Updated: Aug 18 2022

# Objective
The objective of this document is outline and mitigate the risks for Plant Pals operations launch.

Executive Summary
We are expecting to launch our new project Plant Pals service this year.
This service includes a new website and management of delivery of plants to clients.
Major risks include going over budget and schedule delays.

RISK TYPE ONE: Going over the project budget

Scenario	Risk to project (L/M/H)	Mitigation Plan
A product vendor loses a product shipment	LOW	Accept this risk by making a contingency plan on how to satisfy or reimbursing any of our customers
A product vendor charges a higher rate than expected	MEDIUM	Reduce the risk by getting cost estimates from multiple providers
Purchase of 2x 16,000$ / initially quoted delivery trucks	HIGH	Transfer the risk by consulting with the appropriate stakeholders/SME's to insure that our largest upfront purchase will be fully equipped, capable and up to industry standard

RISK TYPE TWO: Falling behind the training schedule

Scenario	Risk to project (L/M/H)	Mitigation Plan
Employee Trainer gets ill or misses training sessions	LOW	Reduce by having them train an associate on the new protocols for training in case they miss a few days. When one teaches, two learn.
Not enough employees trained in time for launch	MEDIUM	Reduce the liklihood of this by clearing schedule ahead of time and possibly hiring more employees for the new system
Training program destroys data storage infrastructure	HIGH	Avoid – us being the responsible, brilliant and good looking managers we are will insure this will never happen by backing up our data before installing the new training software.

Appendix:

Probability chart:

Probability
	Qualitative
Low	Very low chance of risk occurring.

Medium	Medium chance of risk occurring.
High	High chance of risk occurring.

Impact chart:

Types of Impact	Low	Medium	High
Financial	Low financial impact, / costing the company $0-$14,000	Medium financial impact, / costing the company $15,000-$29,000	High financial impact, / costing the company $30,000 or more
Operational	Low impact to project operations, causing delays of a few days to a few weeks	Medium impact to project operations, / with potential to delay project by a month or more	High impact to project operations, / with potential to cause project failure
People	Low impact to employee attrition, with 5%+ of employees quitting	Medium impact to employee attrition, with 25%+ of employees quitting	High impact to employee attrition, with 50%+ employees quitting

Probability and Impact Matrix:

Inherent Risk
			Impact
			Low	Medium
Probability	High		Medium	High
	Medium		Low	Medium
	Low		Low	Low